PROJECT CHARTER

| Project Title | Artistic Carpets – E-Commerce & Company Website Platform | Phase | Initiation / Charter |
| --- | --- | --- | --- |
| Project Description | Design and development of a public-facing website for a Artistic Carpets. The site will combine company marketing and branding, a home-decor product catalogue, and direct online sales, supported by a separate internal admin panel for tracking manufacturing inventory (wool, chemicals, and other materials). |  |  |
| Project Purpose / Business Case | The company currently has no unified digital presence to support its established US, UK, and European export markets, or its emerging India market (hotel, large-office, and carpet-fitting projects). A professional website with direct e-commerce capability will enable online sales, communicate manufacturing credibility through process transparency, and support customer enquiries across time zones via chatbot and WhatsApp. An internal inventory module will improve visibility of raw-material stock and reorder needs. |  |  |
| Objective (SMART) | Launch a fully functional public website — combining marketing content, product catalogue, and direct online payment — together with an internal inventory-tracking admin panel, within 4–6 weeks of scope sign-off, enabling online sales and chatbot-handled enquiries, and establishing the foundation for a subsequent paid advertising phase (Google, Instagram, Facebook). |  |  |
| Scope | In Scope | Out of Scope |  |
|  |  Public website: company introduction, history, product varieties  Manufacturing process content (first step to final step, with photographs)  Product/material details: 20% cotton / 80% wool; New Zealand and Indian wool sources; chemicals and other |  Cash on delivery  Execution of advertising campaigns (Google, Instagram, Facebook) — scoped as a later phase  Inventory admin panel: separate login, tracks wool/chemicals/materials, flags reorder needs, not visible to public site visitors |  |

|  | materials used  E-commerce: online buying/purchasing functionality with direct payment (Razorpay and other options under evaluation)  Chatbot for continuous website enquiry handling (covers US/UK time-zone gaps)  WhatsApp API integration to distribute website and product catalogue to contacts  Website theme/branding based on existing company logo |  |
| --- | --- | --- |
| Key Deliverables | Deliverable | Description |
|  | Public marketing + e-commerce website | Company info, product catalogue, manufacturing story, and online purchase/payment flow |
|  | Chatbot integration | Automated handling of website enquiries, including outside local business hours |
|  | WhatsApp API integration | Distribution of website link and product catalogue to contact lists |
|  | Inventory admin panel | Separate-login internal tool for material stock tracking and reorder alerts |
|  | Brand theme | Website visual design based on the existing company logo |
|  | Project quotation | Finalized once required business/product/manufacturing details are received |

| Stakeholders | Name | Role | Responsibility |
| --- | --- | --- | --- |
|  | Wassem Ahmad | Project Sponsor (Client) | Provide business, product, manufacturing, and inventory details; approve scope and branding |
|  | Prashant Patil | Project Manager (Nexcore Alliance) | Own delivery, prepare quotation, coordinate development team |
|  | Zaid Acchwa (Team Lead), Mohammed Jagda, Karan Kanakrajan | Develope ment Team | Individual client-side and dev-team roles beyond sponsor |
| Timeline/ Milestones | Milestone | Date | Owner |
|  | Project kickoff meeting, understanding business and goals, discussing all required features, competitor research, finalizing the project scope, collecting branding materials (logo, colors, content, images), planning the project timeline, and obtaining approval before development begins. | Week 1 – Project Planning & Requirem ent Gathering | Client and Nexcore Alliance |
|  | Preparing the website layout and page designs, planning the user journey, designing mobile and desktop views, reviewing the design with the client, planning the database and admin panel structure, and finalizing the complete blueprint for development. | Week 2 – Design & Project Structure | Nexcore Alliance |
|  | Building the website pages, developing the admin panel, setting up product and inventory management, implementing user login and security, adding content management features, and ensuring the website works smoothly across all devices. | Week 3 – Website & Admin Panel Developm ent | Nexcore Alliance |

|  | Integrating the payment gateway, WhatsApp Business, AI chatbot, email notifications, enquiry forms, and other third-party services, followed by testing to ensure all features work together seamlessly. | Week 4 – Integratio ns & Smart Features | Nexcore Alliance |
| --- | --- | --- | --- |
|  | Testing the complete website on different devices and browsers, fixing bugs, uploading products and content, checking all forms and payment flows, client review (UAT), and making any final changes based on feedback. | Week 5 – Testing & Client Review | Client & Nexcore Alliance |
|  | Deploying the website to the live server, connecting the domain and SSL, performing final checks, providing admin panel training, sharing documentation, launching the website, and offering post-launch support for a smooth transition. | Week 6 – Launch & Handover | Nexcore Alliance |
| Resources | Resource Type | Details |  |
|  | Team | Vendor website development team (individual roles not yet assigned); client-side team providing business, product, manufacturing, and inventory content |  |
|  | Infrastructure | Website hosting; payment gateway (Razorpay and other options under evaluation); WhatsApp Business API; chatbot platform |  |
| Risks | Risk | Mitigation |  |
|  | Aggressive 4–6 week timeline for combined website, e-commerce, chatbot, WhatsApp, and inventory panel delivery | Prioritize core website and payment first; phase chatbot, WhatsApp, and inventory panel if the timeline slips |  |

|  | Delay in receiving business/product/manufacturing details and logo from client | Set a firm Week 1 submission deadline for all required content |
| --- | --- | --- |
|  | Payment gateway selection (Razorpay vs. alternatives) not yet finalized | Finalize provider in Week 1 to avoid integration delays |
|  | Inventory module scope was pending client-side confirmation; now confirmed in scope, but detailed requirements are not yet captured | Capture detailed inventory requirements during Week 1 requirements-gathering |
| Assumptions |  Client will supply logo, product/manufacturing content, and inventory details promptly to keep the fast-track timeline  The chosen payment gateway supports international payment collection from US, UK, and EU customers  Advertising (Google, Instagram, Facebook) is a separate, later phase and not part of this build |  |
| Constraints |  4–6 week fast-track delivery window  Cash on delivery explicitly excluded as a payment method  Inventory panel must remain hidden from public site visitors and use separate authentication from the customer-facing website |  |
| Success Criteria |  Website live with full marketing content, manufacturing story, and functioning product catalogue  Direct online payment successfully processing orders (cash on delivery excluded)  Chatbot actively handling enquiries, including outside local business hours  WhatsApp API distributing the website link and catalogue to contacts  Inventory admin panel operational with separate login, tracking material stock and reorder flags |  |

|  |  Quotation finalized and shared once required details are collected |  |  |
| --- | --- | --- | --- |
| Approval / Sign-off | Role | Name | Signature / Date |
|  | Project Sponsor (Client) | Wassem Ahmad |  |
|  | Project Manager (Nexcore Alliance) | Prashant Patil |  |